## Start here
openpm-lens template
Fill in the Tasks sheet, optionally the Settings, Rates, Holidays, Leave, Risks, Issues and Changes sheets, then upload this file to openpm-lens (Import or Portfolio tab). The app recognises it and sets itself up.
Your file stays on your computer: the app runs in your browser and sends nothing anywhere.
Rules that matter
1. One row per task. Do not rename, move or delete the column headings in row 1 of the Tasks sheet.
2. Effort is in HOURS, as plain numbers. Percent is 0 to 100.
3. Dates are year-month-day, for example 2026-03-31, typed as text so Excel will not change them.
4. A blank cell means "not known". It is never treated as 0. Type 0 only when you mean zero.
5. Fill only what you have. Each part of the app tells you what it still needs.
6. Yellow cells are for you to fill in. Cells with a small arrow have a list to pick from.
The Tasks columns
Column | Needed for | What to put there
Project | Optional | Name of the project. Fill it in to see several projects side by side on the Portfolio tab.
Programme | Optional | The programme the project belongs to (used to group projects).
Team | Optional | The team that owns the project.
ID | Recommended | A short unique reference such as T-1. Used to point at a task when something needs fixing.
Task | Required | What the task is called.
Type | Optional | Pick from the list. Needed for the Quality tab: tasks of type Bug are counted as defects.
Status | Required | Pick from the list: Not started, In progress, Done or Cancelled.
Assignee | Optional | Who does the work. Needed for Resources and Cost in money. Separate several people with a semicolon (;).
Planned start | For schedule | Year-month-day, for example 2026-03-02. The plan, not what happened.
Planned finish | For schedule | Year-month-day. The plan, not what happened.
Actual start | For flow | The day work really began. Leave blank if it has not begun.
Actual finish | For flow | The day work really finished. Leave blank if it is not finished.
Estimate (h) | For cost and schedule | Planned effort in HOURS. Plain number. Leave blank if there is no estimate (blank is not the same as 0).
Actual (h) | For cost | Hours really spent so far. Plain number. 0 means "none spent"; blank means "not recorded".
% complete | For cost and schedule | A number from 0 to 100 (write 40, not 40%). Done tasks should be 100.
Created | For quality | The day the item was raised. Year-month-day.
Severity | Optional | For bugs: Critical, High, Medium or Low.
Found in | Optional | Where a bug was found, such as Testing or Production. Lets the Quality tab count problems found after release.

## Tasks
Project | Programme | Team | ID | Task | Type | Status | Assignee | Planned start | Planned finish | Actual start | Actual finish | Estimate (h) | Actual (h) | % complete | Created | Severity | Found in

## Settings
Setting | Value | What it does
Status date |  | The "as of" day for the report, year-month-day. Required for schedule, flow and quality. Never assumed.
Hours per working day | 8 | Used to turn days into hours and to spread planned work over days.
Days counted | Weekdays | Weekdays (Mon-Fri; days on the Holidays sheet are skipped) or All days.
Weekly capacity (h) | 40 | Hours one person can work in a week, for the Resources tab.
Currency |  | A label such as INR or USD. Optional; for the Cost in money tab.
Default hourly rate |  | Rate used for people not listed on the Rates sheet. Optional.
Green from | 0.95 | CPI/SPI at or above this is Green. A starting value, not a standard.
Amber from | 0.85 | CPI/SPI at or above this (but below Green) is Amber; below is Red. A starting value, not a standard.
Progress rule | Use the % complete column | How % complete is decided. The first choice uses the % complete column.
In-progress credit (%) | 50 | Only for the Status-based rule: % credited to tasks that are In progress.
Original budget (h) |  | Hours in the plan before any approved change. Only used to show scope growth on the RAID tab. Optional.
Risk medium from | 7 | A risk score (probability x impact, 1 to 25) at or above this is Medium. A starting value, not a standard.
Risk high from | 13 | A risk score at or above this is High. A starting value, not a standard.

## Rates
Person | Hourly rate | Names must match the Assignee column exactly. Optional.

## Holidays
Date | Name | Days everyone is off (year-month-day). Used when days are counted as Weekdays. Optional.

## Leave
Person | From | To | Days a person is away. Leave "To" blank for a single day. Names must match the Assignee column. Optional.

## Risks
ID | Risk | Probability (1-5) | Impact (1-5) | Owner | Response | Status | Action | Action due | Action done | Optional. Probability and Impact are whole numbers 1 (lowest) to 5 (highest); score = probability x impact. Leave blank if not yet rated: the risk is listed as not scored.

## Issues
ID | Issue | Priority | Owner | Status | Raised | Due | Resolved | Optional. An issue is a problem that has already happened. Age is counted from Raised to the status date (calendar days).

## Changes
ID | Change | Requested by | Decision | Requested | Decided | Cost impact (h) | Schedule impact (days) | Optional. Cost impact in hours and schedule impact in days; use a minus sign for a reduction. Only Approved changes are added up.